## Campaign Calendar
DIGITAL 6IX
Event Marketing Calendar ¦ [CLIENT] ¦ [MARKET] ¦ [EVENT WINDOW]
ASSET |  |  | BUILD |  |  |  | TIMING |  |  |  |  | DISCOVERY
Asset / Task | Sub-event | Phase | Channel | Format | Owner | Status | Go Live Date | T-minus | Expiry Date | Days Live | Takedown | CTA Target | Discovery Prompt | Event Schema | Listing | Priority | Notes
Lineup announcement: full programme page goes live | Festival-wide | Announce | Website | Landing page | Agency | Live | 2026-05-20 | 36 | 2026-07-19 | 60 | Auto | /lineup/ | what films are showing at the film festival in toronto this month | Event | Live | High | EXAMPLE ROW. Delete whenever, the tracker counts from row 6.

## Legend & Tracker
DIGITAL 6IX
Event Marketing Calendar ¦ Legend and campaign tracker
Setup
1. Fill the red-outlined cells below, then update the same client line in row 2 of the Campaign Calendar tab.
2. Row 5 on the Campaign Calendar tab is a filled example. Delete it whenever, the tracker counts from row 6.
3. The tab is banded: ASSET, BUILD, TIMING, DISCOVERY. One row per asset, not per channel.
4. Event Start below drives every T-minus. Set it before you plan anything, or the pacing numbers are meaningless.
5. Every dated asset needs an Expiry Date. A festival site full of screenings that already happened is a site that lies.
Client |  | Red-outlined cells are yours to fill.
Market / geo
Event name
Event start date | 2026-06-25 | Drives the T-minus column. Example dates, replace them.
Event end date | 2026-07-19
On-sale date | 2026-05-01
Column definitions
Column | What it captures | Why it matters
Phase (C) | Announce, On sale, Momentum, Last call, Live, After. | An event campaign is not a content calendar with dates. It is six short campaigns with different jobs. Announce builds a list, On sale converts it, Last call is where most of the revenue actually lands, and After is the one everybody skips.
Go Live Date (H) | When the asset publishes. | The only date most calendars record. On its own it tells you nothing, which is why the next column exists.
T-minus (I) | Days between go live and the event start. Calculated. | The spine of the file. Event marketing is measured backwards from a fixed date, not forwards from a month. Green is fourteen or more days out. A plan that is mostly amber and orange is not a plan, it is a fortnight of panic with a spreadsheet attached.
Expiry Date (J) | The day this asset stops being true. | The column nobody has. A content calendar plans publishing. An event calendar has to plan unpublishing, because a screening that has already happened, a sold-out ticket link, and a lineup that changed are all lies your site is still telling, to the audience and to the engines reading it.
Takedown (L) | Auto, Manual, Archive, Evergreen, or None. | How the asset disappears. Auto means the site handles it, which is the only answer that survives a busy festival week. None is red because None means a human has to remember, and during a live event nobody remembers.
CTA Target (M) | The page this asset sends people to. | Decide before you build. Assets pointing at the homepage because nobody chose are how a campaign quietly loses its own funnel.
Discovery Prompt (N) | The question a real person asks that this asset should answer. | The GEO layer. Nobody types your festival name into an assistant before they know it exists. They type 'what is on in Toronto this weekend' and 'things to do in the distillery district'. If nothing you publish answers that sentence, you are only findable by people who already found you.
Event Schema (O) | The JSON-LD type on the page. | Event and SubEvent are the only reason a listing surface or an assistant can parse a date, a venue and a price without guessing. None is red. For a multi-day festival with sub-events, this is not optional, it is the whole discovery mechanism.
Listing (P) | Whether the event is submitted to the listing sites that matter. | Assistants answering 'what is on this weekend' quote listing sites and local press far more than they quote your own domain. Missed carries brand red: it is the cheapest reach in event marketing and the easiest to forget.
Priority (Q) | High, Medium, Low. | High carries brand red. It is not a compliment, it is the row that will hurt if it slips.
Dropdown options and their colours
Phase (C) |  | Last call is orange on purpose. It is the highest-converting window and the one that gets planned last.
Announce
On sale
Momentum
Last call
Live
After
Owner (F) |  | Client rows carry brand red: approvals, artwork and lineup confirmations are what stall an event build.
Agency
Client
Writer 1
Designer
AI
Status (G) |  | Hold is brand red. During an event window a held asset is a decision nobody has made yet.
Planned
In progress
In review
Scheduled
Live
Done
Hold
T-minus (I) |  | Fourteen days or more is green. Under seven is orange. Read the spread, not the rows.
14 and up
7 to 13
1 to 6
Event day or after
Takedown (L) |  | None is red. It means a human has to remember during the busiest week of the year.
Auto
Manual
Archive
Evergreen
None
Event Schema (O) |  | None is red. Without Event markup a listing surface has to guess your dates.
Event
SubEvent
FAQPage
Offer
None
Listing (P) |  | Missed carries brand red. Free reach you forgot to claim.
Not needed
To submit
Submitted
Live
Missed
Priority (Q) |  | If everything is High, nothing is.
High
Medium
Low
Tracker (live)
BUILD
Assets planned | 0
Live | 0
Scheduled | 0
In progress | 0
On hold | 0
Client-owned rows (dependencies) | 0 | The rows that stall. Chase these first, they are not yours to finish.
Percent live or done | 0%
PACING |  | Event marketing is measured backwards. This is the section that tells you whether you have a plan or a panic.
Assets 14+ days out | 0
Assets 7 to 13 days out | 0
Assets in the final 6 days | 0
Assets on or after event day | 0
Final-week share | 0% | The panic metric. If a third of the campaign goes live in the last six days, the campaign is the last six days.
Earliest asset (T-minus) | 0
Average T-minus | 0
LIFECYCLE |  | What a content calendar never asks: when does this stop being true, and who takes it down.
Assets with an expiry date | 0
Expiry coverage | 0%
Takedown set to None | 0 | Each of these is a human who has to remember something during the busiest week of the year.
Auto-takedown coverage | 0%
Past expiry but still marked Live | 0 | Should be zero. Anything here is on your site right now, telling people about something that already happened.
DISCOVERY |  | Nobody types your event name into an assistant before they know it exists.
Discovery prompts mapped | 0
Prompt coverage | 0%
Event or SubEvent schema | 0
Schema set to None | 0
Listings live | 0
Listings still to submit | 0
Listings missed | 0 | Free reach you did not claim. The cheapest number on this tab to fix.
PHASE MIX |  | Last call is where the revenue lands. Count the rows and see whether you planned for that.
Announce | 0
On sale | 0
Momentum | 0
Last call | 0
Live | 0
After | 0
CHANNEL MIX
Website | 0
Email | 0
Instagram | 0
TikTok | 0
Facebook | 0
Paid social | 0
Paid search | 0
PR | 0
Partner | 0
Influencer | 0
Print | 0
Listing | 0
Notes
One row per asset, not per channel. The same story pushed on Instagram and in an email is two rows, because they go live on different days and expire on different days.
T-minus reads from Event start on this tab. Change that one cell and the whole pacing section re-reads.
Past expiry but still marked Live uses TODAY(), so it re-checks every time you open the file. It is the closest thing here to an alarm.
Listing sites and local press are what assistants quote for 'what is on this weekend'. Treat the Listing column as a distribution channel, not admin.
Dropdown and tracker ranges run to row 155. Add rows past that and you must extend both.
Fonts are Noto Sans and Roboto to match the site. Google Sheets has both natively, Excel falls back if they are not installed locally.
Digital 6ix ¦ digital6ix.ca ¦ Free to use, edit, and share.